Exercise IV – POSSIBLE SCENARIO

1. Workload

Documentation

Translation: 30,000 / 2,500 = 12 days

Revision: 30,000 / 7,500 = 4 days

DTP: 100 / 8 = 12.5 hours = 1.5 days

2. Resources

As 12 working days means more than 2 weeks including weekends, we can decide to work with 2 translators. Translation can therefore be finished after 6 days.

One reviser will suffice. One person will be in charge of the DTP.

3. Overlapping

As soon as some files are translated, Revision can start.

For instance, Revision can start 2 days before the end of the translation.

4. Planning Representation

Revision – 4 days

DTP – 1.5 day

Translation – 6 days